## C-02-0009 - BuzzI Drawing List
Project/Proposal Number | Supplier | Discipline | Document Type | Document SubType | Equipment ID | Drawing Number | Filename | Sheet | Latest Rev | Latest Dwg/Rev Date | Old Rev | Description - Eng |  | TPC | Transmittal Purpose Code (TPC) | DSC | Document Status Code (DSC) | Transmittal | Transmittal Date | Transmittal To: | Engineering Release
C-02-0009 | KHD | MECHANICAL | ME | 10 | EQUIPMENT - 038 - SKS Fan | SKS Fan - Datasheet | SKS Fan - Datasheet.pdf | 007 SHEETS | 00 | 2025-05-28 | FALSE | SKS Fan Datasheet | C-02-0009 - Buzzi Alamo FM3 | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-013 | 2026-02-27 | BUZZI, KHD-ATL | 038 - SKS Fan
C-02-0009 | KHD | CIVIL / STRUCTURAL | RC | 02 | Site Survey | 13943 | ACAD-13943-00 Survey Points (260218)-Model.dwg | 001 | 00 | 2026-02-18 |  | Site Survey Control Points |  | A | INFORMATION | F | REFERENCE | Transmittal C-02-0009-006 | 2026-02-19 | BUZZI, KHD-ATL | Site Survey
C-02-0009 | KHD | MECHANICAL | ME | 13 | EQUIPMENT - 098 - VS Separator | 202-001-000079 | 202-001-000079-000-01-00-T011000238603.PDF | 001 | 00 | 2016-09-28 |  | VS outline drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-003 | 2026-02-12 | BUZZI, KHD-ATL | 098 - VS Separator
C-02-0009 | KHD | MECHANICAL | ME | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-001 | 31510224_acm_001_00.dwg & pdf | 001 | 00 | 2026-03-06 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-002 | 31510224_acm_002_00.dwg & pdf | 002 | 00 | 2026-03-06 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-003 | 31510224_acm_003_00.dwg & pdf | 003 | 00 | 2026-03-06 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-004 | 31510224_acm_004_00.dwg & pdf | 004 | 00 | 2026-03-06 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-005 | 31510224_acm_005_00.dwg & pdf | 005 | 00 | 2026-03-06 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-006 | 31510224_acm_006_00.dwg & pdf | 006 | 00 | 2026-03-06 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-007 | 31510224_acm_007_00.dwg & pdf | 007 | 00 | 2026-03-06 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-008 | 31510224_acm_008_00.dwg & pdf | 008 | 00 | 2026-03-05 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-009 | 31510224_acm_009_00.dwg & pdf | 009 | 00 | 2026-03-06 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-010 | 31510224_acm_010_00.dwg & pdf | 010 | 00 | 2026-03-06 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510224-011 | 31510224_acm_011_00.dwg & pdf | 011 | 00 | 2026-03-06 |  | General Arrangement - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-014 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Feed
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510596_001 | 31510596_acm_001_00.dwg & pdf | 001 | 00 | 2026-03-06 |  | General Arrangement - Cement Silo - General Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-015 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Product Area
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510596_002 | 31510596_acm_002_00.dwg & pdf | 002 | 00 | 2026-03-06 |  | General Arrangement - Cement Silo - Section View |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-015 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Product Area
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510596_003 | 31510596_acm_003_00.dwg & pdf | 003 | 00 | 2026-03-06 |  | General Arrangement - Cement Silo - Section View |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-015 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Product Area
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510596_004 | 31510596_acm_004_00.dwg & pdf | 004 | 00 | 2026-03-06 |  | General Arrangement - Cement Silo - Section View |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-015 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Product Area
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510596_005 | 31510596_acm_005_00.dwg & pdf | 005 | 00 | 2026-03-06 |  | General Arrangement - Cement Silo - Section View |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-015 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Product Area
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510596_006 | 31510596_acm_006_00.dwg & pdf | 006 | 00 | 2026-03-06 |  | General Arrangement - Cement Silo - Section View |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-015 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Product Area
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510596_007 | 31510596_acm_007_00.dwg & pdf | 007 | 00 | 2026-03-06 |  | General Arrangement - Cement Silo - Eqpt Plan +0.000M LVL |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-015 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Product Area
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510596_008 | 31510596_acm_008_00.dwg & pdf | 008 | 00 | 2026-03-06 |  | General Arrangement - Cement Silo - Eqpt Plan +300 & +5200M LVL |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-015 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Product Area
C-02-0009 | KHD | MECHANICAL | GA | 10 | GENERAL ARRANGEMENTS | 244-024-31510596_009 | 31510596_acm_009_00.dwg & pdf | 009 | 00 | 2026-03-06 |  | General Arrangement - Cement Silo - Eqpt Plan |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-015 | 2026-03-06 | BUZZI, KHD-ATL | General Arrangement - FM3 Product Area
C-02-0009 | KHD | MECHANICAL | ME | 13 | EQUIPMENT - 067 - Ball Mill | 308-001-131505131 | 31505131.pdf | 001 | 00 |  |  | Ball Mill outline drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-003 | 2026-02-12 | BUZZI, KHD-ATL | 067 - Ball Mill
C-02-0009 | KHD | MECHANICAL | ME | 13 | EQUIPMENT - 059 - Hot Gas Generator | 311-018-000042 | 311-018-000042-BL2-Rev01-BA Brennkammer.pdf | 002 | 01 | 2017-01-24 |  | HGG outline drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-003 | 2026-02-12 | BUZZI, KHD-ATL | 059 - Hot Gas Generator
C-02-0009 | KHD | MECHANICAL | ME | 13 | EQUIPMENT - 038 - SKS Fan | 341-001-031518217_1 | 341-001-031518217_1.pdf | 001 | 00 | 2026-02-23 |  | SKS Fan outline drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-010 | 2026-02-23 | BUZZI, KHD-ATL | 038 - SKS Fan
C-02-0009 | KHD | MECHANICAL | ME | 13 | EQUIPMENT - 038 - SKS Fan | 341-001-031518217_2 | 341-001-031518217_2.pdf | 002 | 00 | 2026-02-23 |  | SKS Fan Foundation Loads |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-010 | 2026-02-23 | BUZZI, KHD-ATL | 038 - SKS Fan
C-02-0009 | KHD | MECHANICAL | ME | 13 | EQUIPMENT - 097 - SKS Separator | 366-001-000062 | 366-001-000062-03-001-ACM-030543283_DE.PDF | 001 | 03 | 2014-01-31 |  | SKS outline drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-003 | 2026-02-12 | BUZZI, KHD-ATL | 097 - SKS Separator
C-02-0009 | KHD | MECHANICAL | ME | 13 | EQUIPMENT - 069 - Roller Press | 375-001-031507112-01-001 | 375-001-031507112-01-001-ACM_DE_Rollenpresse.pdf | 001 | 00 | 2026-02-02 |  | Roller Press Outline Drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-010 | 2026-02-23 | BUZZI, KHD-ATL | 069 - Roller Press
C-02-0009 | KHD | MECHANICAL | ME | 13 | EQUIPMENT - 069 - Roller Press | 375-001-031507112-01-002 | 375-001-031507112-01-002-ACM_DE_Rollenpresse.pdf | 002 | 00 | 2026-02-02 |  | Roller Press Hydraulic Unit |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-010 | 2026-02-23 | BUZZI, KHD-ATL | 069 - Roller Press
C-02-0009 | KHD | MECHANICAL | ME | 13 | EQUIPMENT - 069 - Roller Press | 375-001-031507112-01-003 | 375-001-031507112-01-003-ACM_DE_Rollenpresse.pdf | 003 | 01 | 2026-02-02 |  | Roller Press Foundation Loads |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-010 | 2026-02-23 | BUZZI, KHD-ATL | 069 - Roller Press
C-02-0009 | KHD | MECHANICAL | ME | 13 | EQUIPMENT - 010 - Bins | 376-003-131105581 | 376-003-131105581-00-001-IDW_EN.pdf | 001 | 00 | 2022-11-30 |  | RP Pre-Bin outline drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-003 | 2026-02-12 | BUZZI, KHD-ATL | 010 - Bins
C-02-0009 | REDECAM | MECHANICAL | ME | 13 | EQUIPMENT - 039 - Ball Mill Vent Fan | aap - gr - pr | Ball Mill Filter Fan_54.pdf | 001 | 01 | 2026-02-17 |  | SKS Fan outline drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-010 | 2026-02-23 | BUZZI, KHD-ATL | 039 - Ball Mill Vent Fan
C-02-0009 | KHD | MECHANICAL | 00 |  | Design Documents | Basic Design Data | Basic Design Data.pdf | 005 SHEETS | 00 | 2025-06-13 |  | Basic Design Data |  | A | INFORMATION | F | REFERENCE | Transmittal C-02-0009-005 | 2026-02-13 | BUZZI, KHD-ATL | SPECIFICATION
C-02-0009 | REDECAM | MECHANICAL | ME | 13 | EQUIPMENT - 083 – Process Filters | BF-A6-01 | P25060183_BF-A6-01_02.pdf | 001 | 02 | 2026-02-23 |  | BM Process Filter Outline Drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-012 | 2026-02-25 | BUZZI, KHD-ATL | 083 – Process Filters
C-02-0009 | REDECAM | MECHANICAL | ME | 13 | EQUIPMENT - 083 – Process Filters | BF-A6-02 | P25060183_BF-A6-02_02.pdf | 001 | 02 | 2026-02-24 |  | SKS Process Filter Outline Drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-012 | 2026-02-25 | BUZZI, KHD-ATL | 083 – Process Filters
C-02-0009 | KHD | MECHANICAL | ME | 04 | LISTS - Equipment List | BUU Equip List for Tag definition | BUU Equip List for Tag definition.xls | 07 SHEETS | A | 2026-02-06 |  | Tag definition as customer standard tags |  | G | IN PROGRESS | B | IN PROGRESS | Transmittal C-02-0009-002 | 2026-02-06 | BUZZI, KHD-ATL | Equipment List
C-02-0009 | KHD | MECHANICAL | 00 |  | Design Documents | C-02-0009 - Aux Equip Design Safety Factors | C-02-0009 - Aux Equip Design Safety Factors R1.docx | 002 SHEETS | 01 | 2026-02-19 |  | Auxiliary Equipment Design Safety Factors |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-007 | 2026-02-19 | BUZZI, KHD-ATL | SPECIFICATION
C-02-0009 | KHD | MECHANICAL | 00 |  | Design Documents | C-02-0009 - Material properties | C-02-0009 - Material properties R1.xlsx | 001 SHEET | 01 | 2026-02-19 |  | Material Properties |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-007 | 2026-02-19 | BUZZI, KHD-ATL | SPECIFICATION
C-02-0009 | KHD | MECHANICAL | 00 |  | Design Documents | C-02-0009 Design Criteria | C-02-0009-Design Criteria R1.docx | 017 SHEETS | 01 | 2026-02-23 |  | Design Criteria |  | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-011 | 2026-02-23 | BUZZI, KHD-ATL | SPECIFICATION
C-02-0009 | KHD | MECHANICAL | 00 |  | Design Documents | C-02-0009 PAINT SPEC | C-02-0009 PAINT SPEC_0.xlsx | 001 SHEET | 00 | 2025-09-18 |  | Paint Specification |  | A | INFORMATION | F | REFERENCE | Transmittal C-02-0009-005 | 2026-02-13 | BUZZI, KHD-ATL | SPECIFICATION
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-MFS_M-FS-0000 THRU M-FS-5700 | C-02-0009-MFS_RevA_021826.pdf | 10 SHEETS | A | 2026-02-18 |  | Mechanical Flowsheet (SEE BELOW) |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-M-FS-0000_01 | C-02-0009-MFS_RevA_021826.pdf | 001 | A | 2026-02-18 |  | Mechanical Flowsheet - Cover Sheet |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-M-FS-4300_01 | C-02-0009-MFS_RevA_021826.pdf | 002 | A | 2026-02-18 |  | Mechanical Flowsheet - 4300 - Ground Limestone & Slag 4000 - Raw Material Handling |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-M-FS-5100_01 | C-02-0009-MFS_RevA_021826.pdf | 003 | A | 2026-02-18 |  | Mechanical Flowsheet - 5100 - Feeding & Dosing 5000 - Cement Preparation |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-M-FS-5100_02 | C-02-0009-MFS_RevA_021826.pdf | 004 | A | 2026-02-18 |  | Mechanical Flowsheet - 5100 - Feeding & Dosing 5000 - Cement Preparation |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-M-FS-5100_03 | C-02-0009-MFS_RevA_021826.pdf | 005 | A | 2026-02-18 |  | Mechanical Flowsheet - 5100 - Feeding & Dosing 5000 - Cement Preparation |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-M-FS-5300_01 | C-02-0009-MFS_RevA_021826.pdf | 006 | A | 2026-02-18 |  | Mechanical Flowsheet - 5300 - Roller Press Plant 5000 - Cement Preparation |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-M-FS-5300_02 | C-02-0009-MFS_RevA_021826.pdf | 007 | A | 2026-02-18 |  | Mechanical Flowsheet - 5300 - Roller Press Plant 5000 - Cement Preparation |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-M-FS-5400_01 | C-02-0009-MFS_RevA_021826.pdf | 008 | A | 2026-02-18 |  | Mechanical Flowsheet - 5400 - Cement Gridning Plant 5000 - Cement Preparation |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-M-FS-5600_01 | C-02-0009-MFS_RevA_021826.pdf | 009 | A | 2026-02-18 |  | Mechanical Flowsheet - 5600 - Hot Gas Generator 5000 - Cement Preparation |  | B | REVIEW | A | INFORMATION | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | KHD | MECHANICAL | ME | 01 | FLOWSHEETS - MFS | C-02-0009-M-FS-5700_01 | C-02-0009-MFS_RevA_021826.pdf | 010 | A | 2026-02-18 |  | Mechanical Flowsheet - 5700 - Cement Cooling and Transport 5000 - Cement Preparation |  | B | REVIEW | A | IN PROGRESS | Transmittal C-02-0009-008 | 2026-02-18 | BUZZI, KHD-ATL | FLOWSHEETS - MFS
C-02-0009 | CHRISTIAN PFEIFFER | MECHANICAL | ME | 13 | EQUIPMENT - 016 - Cement Cooler | CP338500 | CP338500 2 0 0.pdf | 002 | 00 | 2020-05-05 |  | Cement Cooler Outline Drawing |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-012 | 2026-02-25 | BUZZI, KHD-ATL | 016 - Cement Cooler
C-02-0009 | KHD | MECHANICAL | 00 |  | Design Documents | Document Control | Document Control 9-8-2025_.docx | 002 SHEETS | 00 | 2025-09-08 |  | Document Control |  | A | INFORMATION | F | REFERENCE | Transmittal C-02-0009-005 | 2026-02-13 | BUZZI, KHD-ATL | SPECIFICATION
C-02-0009 | KHD | MECHANICAL | ME | 03 | FLOWSHEETS - PFS | T16-0126-1-001 | 2026-03-13_Buzzi-Texas_CMnew_D8R15_COM_20-3750_SFGs_BM46_OPC265_heatbalance + flow + data sheets.pdf | 022 SHEETS | D8R15 | 2026-03-13 |  | Process Flow Sheet - Buzzi Texas - New cement mill |  | A | INFORMATION | F | REFERENCE | Transmittal C-02-0009-017 | 2026-03-17 | BUZZI, KHD-ATL | FLOWSHEETS - PFS
C-02-0009 | REDECAM | MECHANICAL | ME | 10 | EQUIPMENT - 039 – Ball Mill Vent Fan |  | Redecam_FAN_900RPM_datasheet.pdf | 003 SHEETS | NA |  |  | Ball Mill Vent Fan Technical Data |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-012 | 2026-02-25 | BUZZI, KHD-ATL | 039 – Ball Mill Vent Fan
C-02-0009 | REDECAM | MECHANICAL | ME | 10 | EQUIPMENT - 083 – Process Filters |  | SPDZ_KHD 5313BF01 SKS BH - R3.pdf | 001 | 03 | 2026-02-19 |  | SKS Process Filter Datasheet |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-012 | 2026-02-25 | BUZZI, KHD-ATL | 083 – Process Filters
C-02-0009 | REDECAM | MECHANICAL | ME | 10 | EQUIPMENT - 083 – Process Filters |  | SPZ_KHD 5417BF01 Cement Mill BH - R3.pdf | 001 | 03 | 2025-09-02 |  | BM Process Filter Datasheet |  | A | INFORMATION | A | PRELIMINARY | Transmittal C-02-0009-012 | 2026-02-25 | BUZZI, KHD-ATL | 083 – Process Filters
C-02-0009 | REDECAM | MECHANICAL | ME | 10 | EQUIPMENT - 050 Nuisance Filters | P25060183 - Nuisance BF - Technical Data | P25060183 - Nuisance BF - KHD Buzzi Alamo - San Antonio TX - Rev.6 - Technical Data.pdf | 001 | 06 | 2026-03-10 | FALSE | Nuisance Filters Datasheet | C-02-0009 - Buzzi Alamo FM3 | C | APPROVAL | A | PRELIMINARY | Transmittal C-02-0009-016 | 2026-03-12 | BUZZI, KHD-ATL | 050 – Nuisance Filters